## Tracker
Serial# | Task Name | Estimated effort (PD) | Owner | Planned Start date | Planned End date | Actual Start date | Actual End date | Status | Remarks
1 | Literature survey | 5 | Tejesh | 2020-03-03 | 2020-03-15 | 2020-03-03 |  | In Progress
2 | Define business questions to be answered | 3 | [6 empty] | Hemant to prepare the Lucidchart flow for the GUI
3 | Data pre-processing | 2
4 | Data visualization | 2
5 | Model build | 2
6 | Model validation and evaluation | 1
7 | Apply different algorithms | 2
8 | Comparative analysis of mutiple different algorithms | 2
9 | Complie results in Tabular format in terms of accuracy score | 1
10 | Summarize results | 1
11 | Creating an API of model | 1
12 | Deploy the solution in live environment (Productionize the solution) | 1
| Total | 23
Note on C1: Prasanta Kundu: PD - #Person days consumed by a single resource
Note on D1: Prasanta Kundu: Name of the resource who is responsible for delivering the task
Note on I1: Prasanta Kundu: It could be - To Do, In Progress, In Review, Done, On hold

## Gantt Chart
Serial# | Task Name | Days since start | Days left for completion
| Literature survey | 0 | 3
| Design thinking solution options | 3 | 4
| Feasibility study | 7 | 2
| Define workflows | 9 | 3
| Identification of search key words in a document and creation of corpus of words (Task 1) | 12 | 3
| Clustering of documents based on search key words (Task 2) | 15 | 3
| Implementation of tagging and matching with search key words (Task 3) | 18 | 3
| Test the solution with a new data input | 21 | 2
| Deploy the solution in live environment (Productionize the solution) | 23 | 2